## Sheet1
Number | Task | Responsibility | Estimated Time | Actual time
Milestone 1
1. Communication:
1.1 | Set up a primary communication tool. | Team
1.2 | Establish communication guidelines. | Team
2. Decision Making:
2.1 | Determine at least two APIs for the project. | Team
2.2 | Determine primary development framework. | Team
3. Repository Management:
3.1 | Create and connect to a GitHub repository. | Ian
3.2 | Draft README file. | Brian
3.3 | Ensure proper branch management | Team
4. Project Planning
4.1 | Work Breakdown
4.1.1 | Create Work Breakdown Structure | Ian
4.1.2 | Prioritize dependencies and importance. | TO DO
4.2 | Scheduling
4.2.1 | Design a detailed project timeline. | Brain
4.2.2 | Schedule regular team meetings and update sessions. | Brian
4.3 | Github Management
4.3.1 | Initiate a GitHub project within the repository. | Ian?
4.3.2 | Write tickets (GitHub Issues) based on the WBS. | TO DO
4.3.3 | Link issues to corresponding milestones and project boards. | TO DO
4.4 | Project Description
4.4.1 | Definine Project objectives | Melvin
4.4.2 | Project scope | Melvin
5. Design
5.1 | Interface Design
5.1.1 | Create wireframes for all primary user interfaces. | Ian
5.1.2 | Develop high-fidelity prototypes for critical application flows. | Ian
5.2 | Architecture Design
5.2.1 | Develop a DFD (APIs and application). | Ian
5.2.2 | Draft architectural diagram (project's backend and frontend) | TO DO
Project Report
1 | Overview of the project | Melvin
2 | Outline which SDLC model was chosen and why | Chris
3 | 2 User stories per each API (4 total, 1 mark each) | Chris
4 | Outline your technology stack and why you chose it | Ian
5 | List of chosen APIs and why you chose them | Chris
6 | Planned features - in detail 3 per API | Chris
7 | Work breakdown structure (WBS) and assigned taks (inc. Report & pressi) | Ian
8 | Project schedule/timeline | Brian
9 | Wireframes and prototype elements for the application interface | Ian
10 | 2 Data flow diagrams (1 high level/overview, 1 with details) (3 marks each) | Ian
11 | Spelling, grammar, table of contents, cover page with links to | Brian
12 | github repository, report cleanliness | Brian
Project Video Pressentation
1 | Overview of the project
2 | Discuss which tech stack / APIs and SDLC model you picked and why
3 | Application features (high-level overview)
4 | Wireframes and prototype elements for the application interface
5 | 1 high level data flow diagram
6 | All members of the group speak, presentation quality
7 | Penalty for going over the allocated 5 minute presenation time limit
8 | Slides formatting
9 | Bullet forms per slide
10 | Images for slides